## Packages
I |  | II |  | III
Ideal for startups or small businesses that need a clean, professional logo and foundational visual identity to get to market quickly. |  | Ideal for established small-to-midsize businesses ready to elevate their brand with more strategic exploration and refined creative development. |  | Ideal for growing businesses that require a robust, scalable brand identity system with expanded creative exploration and versatility across platforms.
Project Kickoff | 650 | Project Kickoff | 650 | Project Kickoff | 1000
Internal Project Kickoff (30 minutes) |  | Internal Project Kickoff (30 minutes) |  | Internal Project Kickoff (30 minutes)
Client Kickoff Call (30 minutes) |  | Client Kickoff Call (30 minutes) |  | Client Kickoff Call (1 hour)
Research & Inspiration |  | Research & Inspiration |  | Research & Inspiration
Inspiration Presentation Call (30 minutes) |  | Inspiration Presentation Call (30 minutes) |  | Inspiration Presentation Call (1 hour)
Brand Design | 4100 | Brand Design | 7500 | Brand Design | 10600
Exploration |  | Exploration |  | Exploration
Logo Sketches (up to 5 hours) |  | Logo Sketches (up to 10 hours) |  | Logo Sketches (up to 15 hours)
Visual Direction Presentation (30 minutes) |  | Visual Direction Presentation (30 minutes) |  | Visual Direction Presentation (1 hour)
Brand Design |  | Brand Design |  | Brand Design
2 logo concepts (16 hours) |  | 2 logo concepts to choose (30 hours) |  | 3 logo concepts to choose (45 hours)
Brand Design Presentation (30 minutes) |  | Brand Design Presentation (1 hour) |  | Brand Design Presentation (1 hour)
Revisions |  | Revisions |  | Revisions
Up to 5 hours of revisions on the selected concept |  | Up to 8 hours of revisions on the selected concept |  | Up to 8 hours of revisions on the selected concept
Final Deliverables | 600 | Final Deliverables | 600 | Final Deliverables | 900
Primary logo in multiple formats: |  | Primary logo in multiple formats: |  | Primary and secondary logos in multiple formats and orientations:
PNG, JPG, SVG, EPS |  | PNG, JPG, SVG, EPS |  | PNG, JPG, SVG, EPS
Social Media Icons |  | Social Media Icons |  | Social Media Icons
Font Files |  | Font Files |  | Font Files
Account & Production Management | 700 | Account & Production Management | 1400 | Account & Production Management | 1900
Account Service |  | Account Service |  | Account Service
Production Management |  | Production Management |  | Production Management
Base Starting Price | 6050 | Base Starting Price | 10150 | Base Starting Price | 14400
See Add-Ons for more options. |  | See Add-Ons for more options. |  | See Add-Ons for more options.
Tier 1 Work Examples |  | Tier 2 Work Examples |  | Tier 3 Work Examples

## Tier 1
Internal Estimate
Client:
TBD
Project:
Branding
Date Estimated:
TBD
Phase | Activity | Task | Description | Team | Hours | Rate | Total | Notes
1. Project Kickoff | Account Service | Internal Project Kickoff | Align the internal team on project goals, timeline, roles, and responsibilities. Review client-provided materials, discuss project vision and strategic direction, confirm deliverables, and identify any potential challenges. | Nick, Kellie, Account Manager | 1.5 | 100 | 150 | 30 min call (3 team members)
1. Project Kickoff | Account Service | Client Kickoff Call | Call with the client to understand their goals, brand vision, and project scope. Review initial findings, confirm objectives, and align on the creative direction to ensure we’re on the same page before moving forward with mood boards and design concepts. | Nick, Account Manager | 1 | 100 | 100 | 30 min call (2 team members)
1. Project Kickoff | Creative Direction | Research & Inspiration | Conduct research on industry trends, competitors, and potential design inspirations. | Nick | 2 | 150 | 300
1. Project Kickoff | Account Service | Inspiration Presentation Call | Presentation and discussion of initial research findings and visual inspiration. | Nick, Account Manager | 1 | 100 | 100 | 30 min call (2 team members)
2. Brand Design | Creative Design | Logo Sketches | Provide loose logo concept sketches, exploring a range of font styles, brand marks, and color palette options. Revisions are not anticipated at this stage; if requested, they will be scoped and estimated separately based on client feedback. Up to 5 hours. | Nick | 5 | 150 | 750
2. Brand Design | Account Service | Visual Direction Presentation | Present directions to the client for feedback. Explain the chosen elements and how they will guide the brand design, ensuring alignment with the project's vision. | Nick, Account Manager | 1 | 100 | 100 | 30 min call (2 team members)
2. Brand Design | Creative Design | Brand Design | Develop 2 logo concepts, including color palettes, typography, and visual mockups. Options to be shown in a designed presentation. |  | 16 | 150 | 2400
2. Brand Design | Account Service | Brand Design Presentation | Present the completed brand designs to the client, walking through each element to explain our design choices and how they align with the brand’s objectives. |  | 1 | 100 | 100 | 30 min call (2 team members)
2. Brand Design | Creative Design | Revisions | Up to 5 hours of revisions on the selected concept. |  | 5 | 150 | 750
4. Final Deliverables | Creative Design | Logo Files | Package logo in multiple formats: PNG, JPG, SVG, EPS | Deb | 2 | 150 | 300
4. Final Deliverables | Creative Design | Social Icons | Resize and package logo for social media channels. | Deb | 1 | 150 | 150
4. Final Deliverables | Creative Design | Font Files | Package and provide all licensed brand fonts in appropriate formats for print and digital use. | Deb | 1 | 150 | 150
5. General | Account Service | Account Management | Provide ongoing coordination and communication between the client and internal team. This includes managing timelines, organizing meetings, responding to client questions, ensuring deliverables stay on track, and maintaining project alignment with goals and expectations. | Account Manager | 5 | 100 | 500
5. General | Production Management | Production Management | Oversee the execution of all project deliverables, ensuring quality, accuracy, and consistency across all brand assets. Manage internal workflows, track progress, coordinate cross-functional team efforts, and maintain alignment with project milestones and creative direction. | Kellie | 2 | 100 | 200
5. General | Formulating New Business | Formulating New Business | TBD |  | 0 | 100 | 0
Total | [6 empty] | 6050

## Tier 2
Internal Estimate
Client:
TBD
Project:
Branding - Tier 2
Date Estimated:
TBD
Phase | Activity | Task | Description | Team | Hours | Rate | Total | Notes
1. Project Kickoff | Account Service | Internal Project Kickoff | Align the internal team on project goals, timeline, roles, and responsibilities. Review client-provided materials, discuss project vision and strategic direction, confirm deliverables, and identify any potential challenges. | Nick, Kellie, Account Manager | 1.5 | 100 | 150 | 30 min call (3 team members)
1. Project Kickoff | Account Service | Client Kickoff Call | Call with the client to understand their goals, brand vision, and project scope. Review initial findings, confirm objectives, and align on the creative direction to ensure we’re on the same page before moving forward with mood boards and design concepts. | Nick, Account Manager | 1 | 100 | 100 | 30 min call (2 team members)
1. Project Kickoff | Creative Direction | Research & Inspiration | Conduct research on industry trends, competitors, and potential design inspirations. | Nick | 2 | 150 | 300
1. Project Kickoff | Account Service | Inspiration Presentation Call | Presentation and discussion of initial research findings and visual inspiration. | Nick, Account Manager | 1 | 100 | 100 | 30 min call (2 team members)
2. Brand Design | Creative Design | Logo Sketches | Provide loose logo concept sketches, exploring a range of font styles, brand marks, and color palette options. Revisions are not anticipated at this stage; if requested, they will be scoped and estimated separately based on client feedback. Up to 10 hours. | Nick | 10 | 150 | 1500
2. Brand Design | Account Service | Visual Direction Presentation | Present directions to the client for feedback. Explain the chosen elements and how they will guide the brand design, ensuring alignment with the project's vision. | Nick, Account Manager | 1 | 100 | 100 | 30 min call (2 team members)
2. Brand Design | Creative Design | Brand Design | Develop 2 logo concepts, including color palettes, typography. Options to be shown in a designed presentation which will result in being the final brand guide. | Nick | 30 | 150 | 4500
2. Brand Design | Account Service | Brand Design Presentation | Present the completed brand designs to the client, walking through each element to explain our design choices and how they align with the brand’s objectives. | Nick, Account Manager | 2 | 100 | 200 | 1 hour call (2 team members)
2. Brand Design | Creative Design | Revisions | Up to 8 hours of revisions on the selected concept. | Nick | 8 | 150 | 1200
4. Final Deliverables | Creative Design | Logo Files | Package logo in multiple formats: PNG, JPG, SVG, EPS | Deb | 2 | 150 | 300
4. Final Deliverables | Creative Design | Social Icons | Resize and package logo for social media channels. | Deb | 1 | 150 | 150
4. Final Deliverables | Creative Design | Font Files | Package and provide all licensed brand fonts in appropriate formats for print and digital use. | Deb | 1 | 150 | 150
5. General | Account Service | Account Management | Provide ongoing coordination and communication between the client and internal team. This includes managing timelines, organizing meetings, responding to client questions, ensuring deliverables stay on track, and maintaining project alignment with goals and expectations. | Account Manager | 10 | 100 | 1000
5. General | Production Management | Production Management | Oversee the execution of all project deliverables, ensuring quality, accuracy, and consistency across all brand assets. Manage internal workflows, track progress, coordinate cross-functional team efforts, and maintain alignment with project milestones and creative direction. | Kellie | 4 | 100 | 400
5. General | Formulating New Business | Formulating New Business | TBD |  | 0 | 100 | 0
Total | [6 empty] | 10150

## Tier 3
Internal Estimate
Client:
TBD
Project:
Branding - Tier 3
Date Estimated:
TBD
Phase | Activity | Task | Description | Team | Hours | Rate | Total | Notes
1. Project Kickoff | Account Service | Internal Project Kickoff | Align the internal team on project goals, timeline, roles, and responsibilities. Review client-provided materials, discuss project vision and strategic direction, confirm deliverables, and identify any potential challenges. | Nick, Kellie, Account Manager | 1.5 | 100 | 150 | 30 min call (3 team members)
1. Project Kickoff | Account Service | Client Kickoff Call | Call with the client to understand their goals, brand vision, and project scope. Review initial findings, confirm objectives, and align on the creative direction to ensure we’re on the same page before moving forward with mood boards and design concepts. | Nick, Account Manager | 2 | 100 | 200 | 1 hour call (2 team members)
1. Project Kickoff | Creative Direction | Research & Inspiration | Conduct research on industry trends, competitors, and potential design inspirations. | Nick | 3 | 150 | 450
1. Project Kickoff | Account Service | Inspiration Presentation Call | Presentation and discussion of initial research findings and visual inspiration. | Nick, Account Manager | 2 | 100 | 200 | 1 hour call (2 team members)
2. Brand Design | Creative Design | Logo Sketches | Provide loose logo concept sketches, exploring a range of font styles, brand marks, and color palette options. Revisions are not anticipated at this stage; if requested, they will be scoped and estimated separately based on client feedback. Up to 15 hours. | Nick | 15 | 150 | 2250
2. Brand Design | Account Service | Visual Direction Presentation | Present directions to the client for feedback. Explain the chosen elements and how they will guide the brand design, ensuring alignment with the project's vision. | Nick, Account Manager | 2 | 100 | 200 | 1 hour call (2 team members)
2. Brand Design | Creative Design | Brand Design | Develop 3 logo concepts, including color palettes, typography, and visual mockups. Options to be shown in a designed presentation. | Nick, Deb | 45 | 150 | 6750
2. Brand Design | Account Service | Brand Design Presentation | Present the completed brand designs to the client, walking through each element to explain our design choices and how they align with the brand’s objectives. | Nick, Account Manager | 2 | 100 | 200 | 1 hour call (2 team members)
2. Brand Design | Creative Design | Revisions | Up to 8 hours of revisions on the selected concept. | Nick | 8 | 150 | 1200
4. Final Deliverables | Creative Design | Logo Files | Package primary and secondary logo in multiple formats, PNG, JPG, SVG, EPS. | Deb | 4 | 150 | 600
4. Final Deliverables | Creative Design | Social Icons | Resize and package logo for social media channels. | Deb | 1 | 150 | 150
4. Final Deliverables | Creative Design | Font Files | Package and provide all licensed brand fonts in appropriate formats for print and digital use. | Deb | 1 | 150 | 150
5. General | Account Service | Account Management | Provide ongoing coordination and communication between the client and internal team. This includes managing timelines, organizing meetings, responding to client questions, ensuring deliverables stay on track, and maintaining project alignment with goals and expectations. | Account Manager | 15 | 100 | 1500
5. General | Production Management | Production Management | Oversee the execution of all project deliverables, ensuring quality, accuracy, and consistency across all brand assets. Manage internal workflows, track progress, coordinate cross-functional team efforts, and maintain alignment with project milestones and creative direction. | Kellie | 4 | 100 | 400
5. General | Formulating New Business | Formulating New Business | TBD |  | 0 | 100 | 0
Total | [6 empty] | 14400

## Add-Ons
Item | Description | Hours | Rate | Total
Brand Asset Library Audit | Inventory of all marketing assets and guidance on what we should update once the final logo is chosen. | 4 | 150 | 600
Additional Concepts | An additional logo concept with color palette and typography. | 15 | 150 | 2250
Design Assistance | Ongoing support for minor design tasks, such as resizing logos, adjusting brand assets, or providing guidance on how to apply brand elements correctly in various applications. | 10 | 150 | 1500
Creative Direction | Oversee designer throughout project. | 5 | 150 | 750
Brand Messaging | Daniel to outline and estimate upon request. | 0 | 150 | 0
Marketing Coordinator | Execution and support of marketing initiatives, including campaign setup, content scheduling, asset organization, and cross-team coordination to ensure timely and accurate delivery. | 2 | 100 | 200
Item | Description | Hours | Rate | Total
0
Essentials PDF Brand Guide | Logo Usage Guidelines Primary logo variations (left aligned, centered, stacked) Social media logos Color Palette Primary brand colors HEX, RGB, CMYK, and Pantone values Typography Primary and secondary fonts Font usage examples (headings, body text) | 0 | 150 | 0
Premium Brand Guide | Logo Usage Guidelines Primary logo variations (left aligned, centered, stacked) Monochrome and full-color applications Social media logos Color Palette Primary and secondary brand colors HEX, RGB, CMYK, and Pantone values Typography Font hierarchy (Headings, subheadings, body text) Font usage examples for digital and print Imagery & Graphic Style Approved photography styles Iconography and graphic elements guidelines Brand Mockups Up to 3 mockups of the logo applied to real-world materials (e.g., business card, social media post, signage, apparel, packaging, etc.) | 0 | 150 | 0