## Audit
Internal Estimate
Client:
Company
Project:
Social Media Audit
Date Estimated:
2026-01-01
Phase | Service | Task | Description | Team | Hours | Rate | Total | Notes / Explanations
1. Audit | Social Media Management | Social Media Audit | Conduct an in-depth social media audit that assesses the effectiveness of your current social media efforts, and those of your main competitors, with the goal of gaining a thorough understanding of both your business and your respective industry as a whole. We will then present our findings to the client for review. | Meg | 4 | 125 | 500
1. Audit | Social Media Management | Social Audit Presentation | Present the Social Media Audit to the client, highlighting key elements and providing guidance on its implementation. | Meg | 1 | 125 | 125
1. Audit | Account Management | Social Audit Presentation | Present the Social Media Audit to the client, highlighting key elements and providing guidance on its implementation. |  | 1 | 100 | 100 | This should be a call that includes Meg, the account manager, Cassidy, sometimes Nick. This should be an hour call.
1. Audit | Production Managment | Production Management | Time dedicated to planning, scheduling, and overseeing the execution of work to ensure the project stays on track, on time, and within scope. | Cassidy | 0 | 100 | 0
1. Audit | Account Management | Account Management | Your Account Manager will coordinate this project with you from start to finish. Their time will include emails, phone calls, and meetings to discuss project details and progress. |  | 0 | 100 | 0
1. Audit | Formulating New Business |  |  |  | 0 | 100 | 0
Total Cost: | [6 empty] | 725

## Onboarding Setup
Internal Estimate
Client:
Company
Project:
Social Media
Date Estimated:
2026-01-01
Phase | Service | Task | Description | Team | Hours | Rate | Total | Notes / Explanations
2. Onboarding | Social Media Management | Social Kick-Off Call | Client/internal kick off call to align on social scope and ongoing monthly content | Meg | 0 | 125 | 0
2. Onboarding | Account Management | Social Kick-Off Call | Client/internal kick off call to align on social scope and ongoing monthly content |  | 0 | 100 | 775 | Client/internal kick off call - limit to a specific timeframe. Include Meg, Account Manager and Production.
2. Onboarding | Social Media Management | Organic Social Setup | Gaining access to client's social platforms, review of any client assets / information, completion of internal documentation, & creation of HeyOrca profile for post scheduling. | Meg | 4 | 125 | 775 | Flat rate for social setup
2. Onboarding | Social Media Management | Paid Social Setup | Setup of social media paid advertising. | Meg | 0 | 125 | 0
2. Onboarding | Social Media Management | NextDoor Social Setup | Setup of NextDoor profile | Meg | 0 | 125 | 0
2. Onboarding | Creative Design | Canva Brand Kit Setup | Creation of Canva Brand Kit including any fonts, colors, logos, photos, graphics. | Erin, Deb | 1 | 150 | 150
2. Onboarding | Creative Design | Light Box Setup | Creation of Light Box to provide to client of approved imagery we can use. | Erin, Deb | 1 | 150 | 150 | 20-30 images
2. Onboarding | Creative Design | Social Graphic Template Design | Initial graphic template set up for creative team | Nick | 0 | 150 | 0 | Initial template design by Nick
2. Onboarding | Creative Direction | Creative Direction | Client/internal kick off call - limit to a specific timeframe | Nick | 0 | 100 | 0
2. Onboarding | Account Management | Account Management | Assist the clients with getting us access to their social accounts for setup. |  | 0 | 100 | 0
2. Onboarding | Marketing Coordinator | Marketing Coordinator | Execution and support of marketing initiatives, including campaign setup, content scheduling, asset organization, and cross-team coordination to ensure timely and accurate delivery. | Emily | 0 | 100 | 0
2. Onboarding | Production Managment | Production Management | Assist the internal team with getting us access to their social accounts for setup, HeyOrca Access, Social Media Overview Documentation. | Cassidy | 0 | 100 | 0
3. Social Profile Setup | Social Media Management | Instagram Page Setup | Creation of new Instagram Page Content to be included: Bio copy (150 characters or less) - What you offer - Who you serve - What makes you different - Call to action Links - Website or link-in-bio URL - Any secondary links if using a link hub Contact Info - Business email - Phone number (optional) - Address (optional for local businesses) Branding Details - Category selection - Display name (can include keyword after brand name) - Username consistency with other platforms | Meg | 0 | 125 | 0 | Coordinate needed information with client for set up. New Social Profile Instructions
3. Social Profile Setup | Creative Design | Instagram Profile Photo | Design of square logo or brand image | Deb, Erin | 0 | 150 | 0
3. Social Profile Setup | Creative Design | Highlight Cover Graphics | Suggested highlight titles: Services Reviews Work / Projects About Contact | Deb, Erin | 0 | 150 | 0 | Optional but recommended
3. Social Profile Setup | Social Media Management | Facebook Page Setup | Creation of new Facebook Page Content to be included: - Business description (short version) - About section copy (long version) - Services list - Mission or positioning statement Links & Contact - Website link - Business phone number - Business email - Street address (if applicable) - Business hours Branding Setup - Business category - Page username - Call-to-action button selection Examples: Call Now, Book Now, Contact Us, Shop Now Admin Access - Page roles assigned to team members - Recovery email set | Meg | 0 | 125 | 0 | Coordinate needed information with client for set up. New Social Profile Instructions
3. Social Profile Setup | Social Media Management | Facebook Page Content Setup | Content at Launch - Welcome post - Service introduction post - Proof post (testimonial or case study) - Promotional or announcement post *To be included in first month of content calendar Messaging Setup - Auto-reply message - Frequently asked questions or quick replies | Meg | 0 | 125 | 0
3. Social Profile Setup | Creative Design | Facebook Profile Photo | Design of square logo or brand image | Deb, Erin | 0 | 150 | 0
3. Social Profile Setup | Creative Design | Facebook Cover Photo | Design of cover photo or banner image | Deb, Erin | 0 | 150 | 0
3. Social Profile Setup | Creative Design | Facebook Pinned Post Graphic | Optional pinned post graphic | Deb, Erin | 0 | 150 | 0
3. Social Profile Setup | Social Media Management | LinkedIn Page Content Setup | Creation of new LinkedIn Page Company Basics - Official company name (exactly as you want it displayed): - Public LinkedIn URL (e.g., linkedin.com/company/yourcompanyname): - Website URL (optional but highly recommended): - Industry: - Company size (range): - Company type (e.g., privately held, nonprofit, partnership, etc.): Company Description - About section (2,000 characters max): Write a concise, engaging summary describing what your company does, your mission, and what makes you different. Tip: Include a few strategic keywords for search visibility. Specialties: Add 5–20 relevant keywords (services, expertise, etc.) Location: Physical address or headquarters location (can hide street if you prefer) Optional but Recommended: - Tagline: A short line under your logo (e.g., “Crafting Digital Experiences That Convert”) - Hashtags: You can select up to 3 “community hashtags” to align your brand with related topics. - Custom button: Choose a CTA (Visit website, Contact us, Learn more, etc.) | Meg | 0 | 125 | 0 | Coordinate needed information with client for set up. New Social Profile Instructions
3. Social Profile Setup | Creative Design | LinkedIn Profile Photo | Logo - Size: 300 × 300 px - Format: PNG or JPG - This will appear as your profile image across LinkedIn. | Deb, Erin | 0 | 150 | 0
3. Social Profile Setup | Creative Design | LinkedIn Cover Photo | - Recommended size: 1128 × 191 px - Use something that represents your brand—your workspace, team, or a clean branded graphic. | Deb, Erin | 0 | 150 | 0
Total Cost: | [6 empty] | 1850

## Ongoing Social
Internal Estimate
Client:
Company
Project:
Social Media
Date Estimated:
2026-01-01
Phase | Service | Task | Description | Team | Hours | Rate | Total | Notes / Explanations
4. Ongoing Monthly | Social Media Management | Organic Social Media Management | # Channels (FB/IG/LI/Etc.) # Posts per Month Strategy and planning Write and schedule content Engagement Monthly OR Quarterly Reporting - Meg to confirm | Meg | 0 | 125 | 0
4. Ongoing Monthly | Social Media Management | Paid Social Media Management | # of Ad Campaigns or Boosted Posts per month Platforms TBD Campaign Type TBD *Meg to confirm if additional creative is needed from team for paid portion. | Meg | 0 | 125 | 0
4. Ongoing Monthly | Social Media Management | NextDoor Social Media Management | Nextdoor advertising connects you with engaged local audiences, perfect for raising awareness, promoting events, and reaching the 55+ community. We handle strategy, monthly execution, and performance reporting to maximize your impact. | Meg | 0 | 125 | 0
4. Ongoing Monthly | Social Media Management | Additional Optional Channels eg. LinkedIn, Pinterest, Instagram, Facebook, TikTok | Meg to list out additional channels recommended and scope of work | Meg | 0 | 125 | 0
4. Ongoing Monthly | Creative Design | Custom Social Graphic Design | Design of custom social posts Social Media Platforms: TBD # of Posts per month: TBD | Erin, Deb | 0 | 150 | 0 | Confirm if Nick wants to design the graphics for month 1, etc. before Deb/Erin takes over Then monthly creative direction time will begin.
4. Ongoing Monthly | Creative Design | Paid Social Ad Design | Design of social media ad - # TBD *Meg to confirm if needed |  | 0 | 150 | 0
4. Ongoing Monthly | Creative Design | NextDoor Ad Design | Design of 1 NextDoor ad | Erin, Deb | 0 | 150 | 0
4. Ongoing Monthly | Social Media Management | Community Engagement | Research of 10-15 target groups, create a custom posting strategy, and manage posting, monitoring, and engagement to promote your business. You’ll receive a detailed Community Engagement Tracking sheet with group insights, rules, a posting plan, content calendar, and performance metrics. Month 1 focuses on research and strategy, with execution starting in Month 2. | Meg | 4 | 125 | 500
4. Ongoing Monthly | Account Management | Ad Hoc Calls/Emails | Handling day-to-day client questions, requests, and updates. |  | 0 | 100 | 0
4. Ongoing Monthly | Account Management | Content Coordination | Gathering Client Assets - Collect photos, videos, promotions, event details, etc. Briefing Creative Team - Provide clear direction, deadlines, and requirements for content creation. Managing Approvals - Send content calendars/posts to client for review, track changes, and secure approval. |  | 0 | 100 | 0
4. Ongoing Monthly | Account Management | Monthly Content Planning Call - Internal | 1 call per month to review strategy, priorities, and campaigns. |  | 2 | 100 | 200 | 1 hour
4. Ongoing Monthly | Account Management | Monthly Planning Call - Client | 1 call per month to review strategy, priorities, campaigns. results, insights, and next month’s plan. |  | 1 | 100 | 100 | 1 hour
4. Ongoing Monthly | Production Managment | Production Management | Updating Project Management Tools - Asana tasks for monthly content cycle, ensuring deadlines are hit. Internal Team Check-ins - Align with copywriters, designers, and strategists on creative direction. Monitoring Progress - Make sure posts are drafted, designed, approved, and scheduled on time. | Cassidy | 0 | 100 | 0
4. Ongoing Monthly | Creative Direction | Creative Direction | Time allocated to establish the overall vision for the project, including brainstorming, concept development, and defining the aesthetic, messaging, and tone. TBD - Nick to confirm depending on how extensive his scope will be | Nick | 0 | 100 | 0
5. Monthly Expenses | Software | Getty Images Monthly Cost | Stock Photo Useage | Getty | - | - | 25 | Included in monthly cost as we will be using stock imagery.
5. Monthly Expenses | Software | HeyOrca Monthly Cost | Social Media post scheduling tool | HeyOrca | - | 59 | 82.6 | Included in monthly cost as calendar is required.
5. Monthly Expenses | Software | Paid Social Advertising Cost | Monthly ad budget of TBD platform(s) | Meta | - | 0 | 0 | Markup 35%
5. Monthly Expenses | Software | NextDoor Advertising Cost | Monthly NextDoor Ad Budget | NextDoor | - | 0 | 0 | Markup 35%
6. Project Padding | Formulating New Business | Formulating New Business | Time dedicated to researching, strategizing, and preparing materials to pursue new business opportunities. This includes discovery, proposal development, estimating, internal planning, and presentation efforts aimed at securing new client partnerships or expanding existing relationships. |  | 0 | 100 | 0
Total Cost: | [6 empty] | 907.6

## Monthly Organic (hidden)
Internal Estimate
Client:
TBD
Project:
TBD
Date Estimated:
TBD
Service | Task | Description | Team | Hours | Rate | Total
Social Media | Organic Social Setup | Gaining access to client's social platforms, review of any client assets / information, completion of internal documentation, & creation of HeyOrca profile for post scheduling. | Meg | - | 175 | 775
Creative Design | Canva Brand Kit Setup | Creation of Canva Brand Kit - including any fonts, colors, logos, photos, graphics. |  | 1 | 150 | 150
Creative Design | Lightbox Setup | Creation of a lightbox to provide to client of approved imagery we can use |  | 1 | 150 | 150
Account Management | Account Management | Your Account Manager will coordinate this project with you from start to finish. Their time will include emails, phone calls, and meetings to discuss project details and progress. |  | 1 | 100 | 100
Production Management | Production Management | Time dedicated to planning, scheduling, and overseeing the execution of work to ensure the project stays on track, on time, and within scope. |  | 1 | 100 | 100
| Project Total |  |  |  |  | 1275
Service | Task | Description | Team | Hours | Rate | Total
Social Media | Social Media Management | Organic Social Media Management | Meg | 12 | 125 | 1500
Social Media | Community Engagement | TBD |  | 4 | 125 | 500
Expense | HeyOrca | Monthly Calendar Subscription |  |  | 59 | 82.6
Creative Design | Monthly Graphic Creation |  |  | 0 | 150 | 0
Creative Direction | Creative Direction | Time allocated to establish the overall vision for the project, including brainstorming, concept development, and defining the aesthetic, messaging, and tone. |  |  |  | 0
Account Management | Account Management | Your Account Manager will coordinate this project with you from start to finish. Their time will include emails, phone calls, and meetings to discuss project details and progress. |  | 0 | 100 | 0
Production Management | Production Management | Time dedicated to planning, scheduling, and overseeing the execution of work to ensure the project stays on track, on time, and within scope. |  | 0 | 100 | 0
| Project Total |  |  |  |  | 2082.6
Notes:
TBD

## Standard Creative Estimates
Item | Description | Team | Hours | Rate | Total | Service | Notes / Explanations
Social
Static Social Graphic |  |  | 1 | 150 | 150 | Creative Design
Animated Social Graphic |  |  | 2 | 150 | 300 | Creative Design
Social Carousel | Max up to 4 slides |  | 3 | 150 | 450 | Creative Design
Notes:
Estimates are based on average, time can fluctuate based on nature of content.