## Photo or Video
Internal Estimate
Client:
TBD
Project:
TBD
Date Estimated:
TBD
Phase | Activity | Item | Description | Team | Hours | Rate | Total | Notes / Explanations
Phase 1. Pre-Production | Account Service | Internal Project Kick-Off Call | Time allocated for the internal team to align on project objectives, deliverables, timelines, and roles before beginning work. |  | 0 | 100 | 0 | This should include Kellie, the account manager and Nick. This call should be limited to 30 or 45 minutes depending on the scope.
Phase 1. Pre-Production | Account Service | Creative briefing and planning session | Initial meeting with the client to align on goals, target audience, messaging, and visual direction for the shoot. |  | 0 | 100 | 0 | This should include the client, the account manager and Nick. This call should be limited to 30 or 45 minutes depending on the scope.
Phase 1. Pre-Production | Creative Direction | Storyboarding / Shot List Creation | Development of a visual plan and detailed list of required shots to guide production and ensure coverage. |  | 0 | 100 | 0 | If this is something Nick would do in a project, I would bill at our Creative Design rate of $150/hr. If he is only overseeing the process, then Creative Direction is good.
Phase 1. Pre-Production | Account Service | Site Walkthrough | Site visit to assess lighting, logistics, and space, to plan optimal setups for filming or photography. |  | 0 | 100 | 0 | This should include Nick and the account manager. Bill to Account Management.
Phase 1. Pre-Production | Production Management | Scheduling and Coordination | Organizing shoot date(s), talent, crew, equipment, and client approvals to ensure a smooth production day. |  | 0 | 100 | 0
Phase 2. Production | Account Service | Oversee Shoot | The Account Manager will be present at the shoot for up to XX hours. |  | 0 | 100 | 0 | Time for the AM to attend the shoot
Phase 2. Production | Photography | 1 full-day photo shoot | Photography up to 8 hours | Nick | 8 | 250 | 2000
Phase 2. Production | Photography Assistant | Photography Assistant | Assistance up to 8 hours |  | 8 | 100 | 800
Phase 2. Production | Creative Direction | Creative Direction | Up to 8 hours | Nick | 8 | 100 | 800 | Add if Nick is attending a video shoot
Phase 2. Production | Photography Assistant | 1 half-day photo shoot | Photography up to 4 hours | Nick | 4 | 250 | 1000
Phase 2. Production | Photography Assistant | Photography Assistant | Assistance up to 4 hours |  | 4 | 100 | 400
Phase 2. Production | Creative Direction | Creative Direction | Up to 4 hours | Nick | 4 | 100 | 400 | Add if Nick is attending a video shoot
Phase 3. Vendor | Vendor | Pre Production | Creative consultation, content planning and pre production
Phase 3. Vendor | Vendor | Equipment
Phase 3. Vendor | Vendor | 1st Shooter Video
Phase 3. Vendor | Vendor | Editing
Phase. 4 Editing | Photography | Editing | TBD | Nick | 0 | 250 | 0
General | Account Service | Account Management | Day-to-day communication, project coordination, and client relationship management. |  | 0 | 100 | 0
General | Production Management | Production Management | Oversight of the website project from initiation through final delivery. This includes task scheduling, timeline management, resource coordination, internal workflow tracking, quality control, and ensuring all project milestones are met. |  | 0 | 100 | 0
General | Marketing Coordinator | Marketing Coordinator | Execution and support of marketing initiatives, including campaign setup, content scheduling, asset organization, and cross-team coordination to ensure timely and accurate delivery. |  | 0 | 100 | 0
General | Formulating New Business | Formulating New Business |  |  | 0 | 100 | 0
5400
Phase | Activity | Item | Description | Total | Notes
General | Raw Footage | Raw Footage | If requested, 50% of project total. | 2700
Notes:

## Rates
Services | Default Description | Rate
Consulting | Strategic guidance and recommendations to shape marketing direction, campaigns, and overall business growth. | 175
Creative Design | Development of visual concepts and graphic assets to support marketing initiatives and campaigns. | 150
Website Design | Planning and designing the look, feel, and user experience of a website to align with brand and business goals. | 150
Website Development | Building and coding functional websites, including custom features, integrations, and responsive layouts. | 150
Photography | Professional photography services to capture branded imagery for use across digital and print platforms. | 250
Photography Assistant | On-site support for photography sessions, including setup, staging, and production assistance. | 100
Copywriting | Writing persuasive, clear, and brand-aligned content for websites, ads, campaigns, and collateral. | 150
Email Marketing | Design, development, and deployment of email campaigns to targeted audiences. | 125
Social Media | Content creation, posting, and campaign management across social platforms. | 125
SEO | Optimization of website structure, content, and keywords to improve visibility and search engine rankings. | 125
Creative Direction | Oversight of the creative vision and execution to ensure consistency across all marketing touchpoints. | 150
Account Management | Day-to-day communication, project coordination, and client relationship management. | 100
Production Management | Coordination of deliverables, vendors, and timelines to ensure smooth execution of projects. | 100
Marketing Coordinator | Execution and support of marketing initiatives, including campaign setup, content scheduling, asset organization, and cross-team coordination to ensure timely and accurate delivery. | 100
Account Strategy | High-level planning and strategic oversight to align marketing efforts with client business goals, budgets, and performance objectives. This includes ongoing analysis, prioritization of initiatives, proactive recommendations, and guidance to ensure all tactics are working together effectively. | 150
Formulating New Business | Identifying opportunities, creating proposals, and developing strategies to secure new client work. (MM/DD/YY - MM/DD/YY) | 100
Vendor Rates and Markups:
Standard Vendor and Media Markups