# Name of Project

### Client:

### Name of Client

### Prepared by:

### Netwave Interactive

# Project Overview

This section should quickly cover the goal, the key deliverables, location, and usage. Below is an example: We’re excited to partner with CLIENT to produce high-quality visual content for use across digital platforms. This project will include a 2-minute brand video showcasing your design process, team, and featured projects, along with a set of 30 professionally edited photos of your latest residential and commercial work. The content will be captured on-site at LOCATION.

The content will be optimized for: TBD match what is in Matty’s contract for example

# Scope of Work

### Pre-Production

- Creative briefing and planning session

- Storyboarding and shot list creation

- Site walk-through (if needed)

- Scheduling and coordination

### Production

- 1 full-day video shoot (up to 8 hours)

- 1 half-day photo shoot (up to 4 hours)

- 2-person crew (director/DP + assistant)

- 4K video camera, gimbal, lav mic kit, softbox lighting

### Post-Production

- Edited 2-minute brand video (with color grading, sound mixing, music licensing)

- 30 edited hi-res photos

- Two (2) rounds of client revisions for video and photos

# Shoot Details

- Primary Location: TBD

- Secondary Location: TBD

- Crew Arrival Time: 8:30 AM

- Estimated Lunch Break: 12:30 PM

- Estimated Wrap Time: 5:00 PM

- Client On-Site Contact: Name + Phone Number

- Purpose of Work: from Matty’s contract

### Client Responsibilities

- Provide access to filming locations and notify any tenants or staff

- Have any on-camera team members available and prepared on shoot day

- Provide timely feedback on drafts within 2 business days of delivery

# Timeline

| Milestone | Date |  |
| --- | --- | --- |
| Pre-production Kickoff | ##### Month 00, 2025 |  |
| Site Walkthrough (if needed) | ##### Month 00, 2025 |  |
| Shoot Date(s) | ##### Month 00, 2025 |  |
| Rain Date | ##### Month 00, 2025 |  |
| First Draft Delivery | ##### Month 00, 2025 |  |
| Final Edits & Delivery | ##### Month 00, 2025 |  |

## Estimate

This estimate was prepared on [DATE].

| Service | Description |  |
| --- | --- | --- |
| Pre-Production | ##### Includes creative briefing, location coordination, scheduling, and development of shot list/storyboard. |  |
| Full-Day / Half-Day Shoot | ##### One X-hour shoot day with a 2-person crew (director/DP and assistant), professional 4K camera, lighting, audio, and stabilization equipment. |  |
| Post-Production | ##### Editing (cutting, color correction, sound mixing), licensed background music, and editing of 30 high-resolution photographs. Includes up to two rounds of revisions. |  |
| Licensed Music Track | ##### Royalty-free music licensed for use in your brand video across web and social platforms. |  |
| TOTAL | $0 |  |

Next Steps & Payment Terms

This estimate will be honored for 30 days from the date above. Price accurate to +/- 10% the price quoted here is only for the work described within this estimate. A 50% deposit is required to commence work. Remaining balance due upon final delivery.

Once the estimate is approved, Netwave will submit a digital copy of the proposal, our Agency Agreement, and a deposit invoice for payment. Upon signature and receipt of payment, the project will commence. If any new requests for development and/or design, new specs, new documents or anything that Netwave hasn’t already seen is brought up after the project has already started, additional costs can be added to the remaining invoices or can be handled in another phase of the project.

# Terms and Conditions

This estimate is governed by the terms and conditions set forth within the Agency Agreement signed by the client. By signing this estimate, the client agrees to those terms and the terms set forth within this document and agrees to pay for services rendered.

If completion of the Company’s obligations under these Terms is prevented or delayed by any act or omission of the Client or its agents, subcontractors, consultants, or employees, Netwave shall not be deemed in breach of its obligations under these Terms or otherwise liable for any costs, charges or losses sustained or incurred by Client.  In each case where the Client delay exceeds 30 days during any phase of the project, the project will be removed from our production schedule and all costs incurred to date will be invoiced to the client at that time, payable upon receipt.  Subsequently, upon continuation of the project, the project will be re-estimated based on the remaining work to be completed. Upon approval, the project shall be placed into our production schedule where it fits at the time.

### Cancellations, Weather, Postponements

Standard Cancellations

- If the Client cancels at any time after the contract is awarded, the 50% deposit will be forfeited.

- If the video shoot is rescheduled for a later date with more than 5 business days' notice, the deposit payment will not be forfeited.

- If the non-weather related cancellation or rescheduling occurs within 5 business days of the scheduled shoot day, 100% of the total job, less editing cost is due. Payment of the cancellation fees and deposit for the new shoot date must be paid to reschedule the shoot.

Weather-Related Postponements for Outdoor Shoots

Each outdoor shoot will have a pre-scheduled rain date. If the shoot is postponed due to weather:

- More than 72 hours before the confirmed shoot date:

  - No penalty will apply.

  - The shoot will move to the pre-scheduled rain date.

  - A new rain date will be mutually agreed upon.

  - The deposit carries over to the new shoot date.

- 48 to 72 hours before the shoot day:

  - The 50% deposit will be forfeited.

  - The shoot will move to the rain date, and a new rain date will be scheduled.

  - A new deposit will be required before the new shoot date.

- Less than 48 hours before the shoot day:

  - A cancellation fee of 100% of the job cost, less editing, will apply.

  - The deposit will be forfeited, and a new invoice for the remaining cancellation fees will be sent and must be paid before the new shoot is scheduled.

  - The shoot will move to the rain date, and a new rain date will be scheduled.

  - Payment of the cancellation fee for the cancelled shoot and a 50% deposit for the rescheduled shoot is required to restart production.

If the shoot is not rescheduled and simply cancelled, the deposit will still be forfeited, and the cancellation fee still applies.

In cases of extreme weather where it would be difficult, impossible, or unsafe for either party to attend the shoot, the shoot will be rescheduled and the deposit will be applied to the new shoot date with no cancellation fee. If the crew is on set and an extreme weather event happens, 100% cancellation fee less editing applies.

### Rights and Ownership

Upon full payment for services rendered, the Creator grants the Agency (and their Client) a non-transferable limited license to use the Work for the purposes outlined in the “Purpose of Work” above.  This license does not grant the Agency’s client any rights to alter, resell or create derivative works with prior written consent.  Raw footage and unedited photos are not included in the deliverables unless specified and may be licensed separately.

### Revisions Policy

Each project includes up to two (2) rounds of revisions to the edited video and/or photo selections. Revisions are limited to reasonable adjustments such as timing, clip swaps, caption edits, or basic retouching. Major changes—including reshoots, restructuring the video concept, or adding new content—are not included and will be subject to additional charges. All revision requests must be submitted within five (5) business days of receiving the draft; delays beyond this window may impact final delivery timelines.

## Signatures

Client Signature: Company Name Date Agency Signature: Netwave Interactive Marketing, Inc. Date

### Sincerely,

Name

Title

Netwave Interactive Marketing, Inc.

email@netwaveinteractive.com